## SD1 STUDENT-CENTERED CURRICULUM
STRATEGIC DIRECTION #1
STUDENT-CENTERED CURRICULUM
Moorpark College will develop and teach inspiring and challenging curriculum that is focused on the academic and career goals of all its students
| GOAL | METRIC |  | PRIORITY FOR 2019-2020 | ACTIONS 2019-2020 | POINT PERSON | LEAD(S) | END OF YEAR STATUS | % COMPLETE | ACTIONS 2020-2021 | POINT PERSON | LEAD(S) | PLANNING RETREAT ACTIONS BRAINSTORM 2020-2021 | Next time: resources requested to implement action | PRIORITIZED RESOURCES ALLOCATED 2020-2021 | GAP
A | Clarify and develop academic programs that effectively lead to student transfer | 1 | Associate Degrees for Transfer available—increase from 29 in 2018-2019 to 31 by 2023-2024 | Y | Develop and launch Computer Science AD-T. | VPAA | Curriculum Co-chairs, Program Specific Deans, faculty level | completed | 100% | promote ADT in Computer Science | VPAA |  | 2019-2020 completed; make sure all departments have an AD-T (applicable programs).
[5 empty] | Develop and launch Civic Engagement AD-T. | VPAA | Curriculum Co-chairs, Program Specific Deans, faculty level | in progress | 50 | complete and submit Social Justice ADT [THEME 1] [THEME 3] | VPAA
|  | 2 | Articulation agreements of CA non-public colleges and universities available—increase from 10 in 2018-2019 to 15 by 2023-2024 | N | National University wants 3 Articulate Agreements | Articulation Officer VP | Articulation Officer, VP, Deans | ongoing | 60 | Explore Arizona University and National University | VPAA |  | 1) Articulate new courses we offer with US/CSU and other non-public universities. 2) Explore options in articulating hybrid lab courses. 3) Use what we had from Guided Pathways to assist students in transferring.
|  | 3 | Degrees aligned with new UC pathways—increase to 5 by 2023-2024 | Y | Develop UC Pathway for Physics | Dean of PS | Department Chair of Physics, Curriculum co-chair, Articulation Officer, Deans | completed | 100 | Explore seven new UC transfer pathways now created: Economics, Mathematics, Business Administration, History, Philosophy, Sociology and Anthropology. Investigate suitability of each for MC and develop curriculum where appropriate.] | Deans of each area |  | 1) Look at the new UC pathways and other colleges and align our own pathways. |  | Mathematics full-time instructor
[5 empty] | Develop UC Pathway for Chemistry | Dean of PS | Department Chair of Chemistry, Curriculum co-chair, Articulation Officer, Deans | completed | 90 | Complete Chemistry pathway | Dean of PS
|  | 4 | Students signing UC TAG agreements—increase from 671 in 2017-2018 to 738 by 2023-2024 | Y | CTE outreach | Dean of CTC | Outreach | ongoing | 60 | CTC expanding marketing effort for TAG. | Dean of CTC |  | 1) Counselors to discuss with students about available TAGs and encourage them to apply. 2) Make the TAG information available on the website. 3) Have instructors make an announcement of the availability of TAGs in class and/or Canvas. 4) TAG syllabus for each silo/discipline (list of all TAGs available in each silo/discipline). 5) Faculty can meet with a counselor about the availability of a TAG for each major then share with students.
B | Improve and expand career education programs ensuring alignment with changing labor market needs | 1 | CTE degrees and certificates available—increase from 29 in 2018-2019 to 34 by 2023-2024 | Y | Offer additional programming in Engineering Tech, Cybersecurity, Cloud, Data Science, Computer Science, Commercial Dance, GIS, Vet Tech. | VPAA | Deans and Chairs of respective areas | many completed | 70 | Complete and promote degrees in Engineering Tech, Cybersecurity, Cloud, Data Science, Computer Science, Commercial Dance, GIS, Vet Tech. | VPAA |  | Ensure that every single class can be transitioned to a hybrid/online class format. |  | CNSE full-time faculty
[5 empty] | Partner with Adult Ed programs to offer program and GE for Respiratory Therapy and Surgical Tech. | VPAA | Deans and Chairs of respective areas | re-evaluate, cost to students too high | 20 | Re-evaluate Adult Ed programs to offer program and GE for Respiratory Therapy and Surgical Tech. | VPAA |  | Each discipline should have a plan to upgrade their curriculum for their ever changing industry. |  | Biology full-time faculty??
|  | 2 | CTE alternative credentials available such as digital badges that lead to certificates —increase from 50 in 2018-2019 to 100 by 2023-2024 | Y | Will complete curricular approval process and offer courses for career exploration badge by spring 2020 | Dean of CTE | CTE Counselor and Career Transfer Center | some progress | 30 | re-assess value to industry of CTE alternative credentials | Dean of CTE |  | Departments/disciplines to assign someone to work with the Dean of CTE to address reaching out to industry to see what changes are happening.
|  | 3 | Pre-apprenticeship programs—increase to 3 by 2023-2024 | Y | Establish pre-apprenticeship programs in Biotech, Applied Manufacturing, Engineering by spring 2020. | Dean of CTE, Job Placer | Career Transfer Center | pilot programs established | 70 | expand biotech program, establish applied manufacturing, engineering, and IT programs | Dean of CTE, Job Placer |  | Inform faculty about expanding the pre-apprenticeship program to other disciplines. Start the conversation in the CTE Workgroup. |  | Biology full-time faculty
C | Create curriculum that supports online student success | 1 | Degrees, certificates, and proficiency awards able to be earned fully online—increase to 35 by 2023-2024 | Y | Using funds from the CVC-OEI grant, complete online programming for Child Development, Business, Accounting, Hospitality, and Public Relations/Journalism | Dean of DE | Deans and Chairs of respective areas, and Dean of DE | completing grant | 80 | Complete online programming for Child Development, Business, Accounting, Hospitality, and Public Relations/Journalism, and explore other potential online degrees | Dean of DE |  | The DE Committee has collected metrics of current online course offerings. This information could be shared and reviewed with departments to create awareness so that online course offerings could be increased. |  | Instructional Technologist/Designer
D | Create curriculum that supports professional improvement | 1 | Noncredit courses for professional improvement— increase from 3 in 2018-2019 to 25 by 2023-2024 | Y | Will complete curricular approval process and offer courses for Entrepreneurship, Career, Theater Lighting, Landscape and Wine for Hospitality by spring 2020 | Dean of CTE, Job Placer | Deans and Chairs of respective areas | Theater lighting completed. Others need to be done. | 20 | Complete curricular approval process and offer courses for Entrepreneurship, Career, Landscape and Wine for Hospitality. Develop additional non-credit programs. Develop process and support for non-credit programs. | Dean of CTE, Job Placer |  | Educate faculty about mirrored courses (Curriculum Committee, VP Council, Senate Council).
E | Provide clear pathways for students through the curriculum | 1 | Fall to spring persistence rates—decrease equity gaps for disproportionately impacted groups by 40% by 2023-2024, and fully close achievement gaps by 2026-2027 | Y | In alignment with the Student Equity Plan: enhance tutoring services connect more students with a student success coach increase awareness of mental health and professional development for faculty provide high impact equity training for faculty Implement Starfish Contact students who dropped and get them re-enrolled for spring | Dean of Counseling | Dean of Counseling, Dean of Tutoring, Student Health Director, Dean of Professional Development, Director of IT, Director of Outreach | Good progress made on most of these initiatives in spite of COVID-19 including contacted EW students | 80 | Implement guided pathways success circles to provide resources needed to students. Expand culturally competent curriculum including exploring requiring ethnic studies [Theme 1] Expand culturally competent student services [Theme 4] Make progress towards having faculty and staff diversity match the diversity of our commmunity and students. Work jointly with HR to review district hiring processes. [THEME 2] | Dean of Counseling |  | Expand Math and Science Center to meet increasing student demand with new furniture and instructional equipment to support learning. - Pull specific equity ideas from program plans and gather in one doument to share with all faculty to facilitate idea sharing. - Educate faculty about the benefits of Starfish to facilitate greater buy-in to implement Starfish.
[5 empty] | Increase usage of ZTC/OER to make textbooks affordable | Dean of Distance Education | Dean of Distance Education | The number of sections using ZTC/OER textbooks from Fall 2019 to Spring 2020 increased by 68 to 172 sections offering ZTC/OER materials | 100% | (1) Formalize ZTC/OER Coordinator role., (2) Create a ZTC/OER mentor program for faculty to consider, review, and adopt OER materials, (3) Develop a marketing campaign to ensure students are aware of ZTC/OER courses, (4) Ensure resources are available to make materials accessible. (5) ensure ZTC resources are culturally relevant [Theme 1] | Dean of Distance Education |  | Formalize ZTC/OER Coordinator role. Create a ZTC/OER mentor program for faculty to consider, review, and adopt OER materials. Develop a marketing campaign to ensure students are aware of ZTC/OER courses. Ensure resources are available to make materials accessible. |  | Marketing Specialist Instructional Technologist/Desgner
|  | 2 | Completion of transfer-level math and English in first year—decrease equity gaps for disproportionately impacted groups by 40% by 2023-2024, and fully close achievement gaps by 2026-2027 | Y | Complete curriculum process for Math M11 and M12 and 900 support courses and offer courses by fall 2020 in compliance with AB705. | Dean of Math & English | Dean and Chair of Math | Math M11 and M12 will be offered in Fall 2020. In addition, we will offer a new Math M915 for support for Statistics. | 100% | (1) Promote and Assess Math M11 and Math M12, (2) Implement MMP, (3) Disaggregate data and address equity gaps Expand culturally competent curriculum [Theme 1] Expand culturally competent student services [Theme 4] Diversify full-time and part-time new hires [Theme 2] | Deans of Math & English |  | Support and review the Math M11 and M12 expansion to best address student needs. Implement Multiple Measures Support district project to support AB705. Assess and disaggregate data from the English and Math courses to ensure equity gaps are addressed. |  | English full-time instructor
F | Continue to develop a body of faculty who are committed to the development of culturally-responsive course content, teaching, and academic counseling methods | 1 | Faculty who participate in high impact equity training once every three years, such as the Equity in the Classroom project, TMOCA, Safe Zone, Project CHESS Faculty Circles, etc.—increase to 100% of full-time and 50% of part-time faculty by 2023-2024, and 100% of part-time faculty by 2028-2029 | Y | Send faculty, staff and administrators to conferences. Include in Faculty Goals & self-Eval. Survey faculty currently involved. Start with baseline. Find ways to incentivize faculty e.g., award, acknowledgement. | VP of SS | VPs, SEA, Deans, PD Committee | Had good attendance in equity hiring training as well as participation in conference attendance | 60% | Follow up on Diversity in Hiring training this year: refining EEO definitions of diversity for hiring committees, brainstorming for interview questions, reviewing district hiring policies to see if they can be improved. [Theme 1] [Theme 2] | VP of SS |  | Identify which trainings count for Flex/Service Hours to further incentivize these trainings. Offer online versions of trainings where possible. More of these trainings should focus on Access and Neuro-atypical students to broaden our equity focus.
|  | 2 | Develop a survey to measure student perception of faculty as culturally-responsive agents of Moorpark College annually | N | Develop the survey | Dean of IE | Dean of IE, President | No progress made, although developed survey related to equity in hiring committee training. | 0% | Implement survey from Community College Equity Leadership Alliance. [Theme 1] [Theme 2] [Theme 4] | Dean of IE
|  | 3 | Course success rates—decrease equity gaps for disproportionately impacted groups by 40% by 2023-2024, and fully close achievement gaps by 2026-2027 | Y | Fully-implement Starfish. Improve equity in the classroom to train specific faculty strategies and best practices working with DI groups, Host and offer 4-6 Professional Development-Faculty/Staff trainings and workshops | VPSS-Starfish Johnny-Student Equity Brian Burns-Professional Development | VPAA | Held 2 trainings on Starfish -- Fall PD and April PD. Held 4 equity-focused PD sessions. | 60% | Increase facutly share-outs from equity events: e.g. CHESS, A2MEND, Student Success Conf. Partner with Student Life to create student-centered equity events Create a workgroup and review at least 25% of curriculum for cultural competency [Theme 1] [Theme 2] [Theme 4] | VPSS, SEA and PD Coordinators VPAA |  | Increase number of courses aligned with CVC-OEI Rubric.
*Themes
Theme 1: Diversifying the Curriculum to Include the History and Culture of Black, Indigenous, LatinX, Asian and other People of Color
Theme 2: Hiring of Staff, Faculty, and Managers that Represent the Racial and Ethnic Diversity of our Student Population
Theme 3: Leadership on Racial Issues and Civic Engagement
Theme 4: Providing Culturally Responsive Student Services such as Counseling, Tutoring, Mental Health, etc

## SD2 STUDENT ACCESS
STRATEGIC DIRECTION #2
STUDENT ACCESS
Moorpark College will provide ready access to a college education for all members of the community it serves
| GOAL | METRIC |  | PRIORITY FOR 2019-2020 | ACTIONS 2019-2020 | POINT PERSON | LEAD(S) | END OF YEAR STATUS | % COMPLETE | ACTIONS 2020-2021 | LEAD(S) | PLANNING RETREAT ACTIONS BRAINSTORM 2020-2021 | PRIORITIZED RESOURCES ALLOCATED 2020-2021 | GAP
A | Increase enrollment of disproportionately impacted groups | 1 | Percentage of applicants that successfully enroll—decrease equity gaps for disproportionately impacted groups by 40% by 2023-2024, and fully close achievement gaps by 2026-2027 | Y | Call students who applied but did not enroll. Also, for students who applied but did not enroll in Business, ECE, and Computer Science, contact those student through various marketing channels including email and Facebook to see if the PACE program could be a better fit for their schedules. | Equity- Johnny Outreach-Alejandra Martinez Marketing-James Schuelke | Director of Outreach and International Relations, Director or Marketing, Dean of PACE | • 841 students called for financial aid phone campaign (students who had submitted a FAFSA for MC but hadn’t applied, we called to help through the enrollment process) • 5,029 students called for PACE (to let them know about this new program available to them • 579 students called that dropped or withdrew from classes due to COVID-19 EW – 579 – reapplied for classes 14% success rate. • 3354 students who had applied for Fall 19 and did not enroll in Fall or Spring 20 – 4.2% application success rate for Summer or Fall 29 (provided support through the registration process and invited to attend the zoom registration event) | 100% | Continue to call students who applied but did not enroll. Work with IE to determine if calls are effective. [Theme 4] Providing Culturally Responsive Student Services such as Counseling, Tutoring, Mental Health |  | Continue outreach work from 2019-20 year. Both in Outreach office and PACE. Have a fully-staffed call center to focus on disporportionately impacted groups. Reach out to students who dropped in Spring 2020 to see how they can continue and advise them of options at the college. Increase the numbers of DI students enrolled in PACE program. Connect with Metrolink officials to increase number of commuting trains coming to Moorpark, consider subsidy for students. Counseling M05 course specifically designed for men of color to improve success and close achievement gap for disproportionately impacted students.
B | Improve and expand courses and services for middle and high school students | 1 | Rising Scholars—Increase from 30 in 2018-2019 to 100 by 2023-2024 |  | Connect with Guided Pathways- Education & Career Alignment workgroup planning. Reach out to middle school counselors. 3 School systems: Simi, Conejo, Las Virgenes. Matricualtion and Dual enrollment work together. Streamline application for dual enrollment. | GP Coordinator | GP Design group 4 | Identified school counselors and students within systems | 60% | Identify and expand cohorts at each of three systems [Theme 2] [Theme 4] |  | Continue support for Rising Scholars program and seek sustainability in preparation for growth next year. Seek grant funding opportunitites.
|  | 2 | Middle school events which are focused on meaningful reflection and action toward pursuing higher education—Increase from 4 in 2017-2018 to 8 by 2023-2024 |  | CTE Week.Connect with Guided Pathways- Education & Career Alignment workgroup planning. | Dean of CTE,GP Coordinator | GTE Workgroup, GP Design Workgroup | conversations starting on EMT | 30 | establish pathway for EMT, Map HS CTE pathways to see where we can grow [Theme 2] [Theme 4] |  | Continue and expand dual enrollment with a second semester counseling courses at middle schools, such as those in LVUSD. Continue and expand CTE Career Week; find ways to increase the number of middle and high school students who can participate.
|  | 3 | Dual enrollment students—Increase from 579 in fall 2017 to 707 by fall 2023 |  | Continue to expand dual enrollment course offerings. Expand CCAP MOU to two additional HS districts. Optimize operations and scheduling. Establish workgroup to optimize student/faculty success. | Dean of Dual | Dean of Dual Enrollment, Deans and Chairs of respective areas, Academic Senate President | Expanded dual enrollment offerings | 80% | Continue to support faculty teaching and advising at high schools with production and promotion of Dual Enrollment Faculty Handbook and regular meetings of DE Advisiory Committee. Coordinate outreach and orientation with Guided Pathway's Education and Career Alignment Design Team. [Theme 1][Theme 2] [Theme 4] |  | Increase Career Education offerings in Dual Enrollment, aligning them with Career Academies at high schools. Recruit qualified faculty to increase dual enrollment offerings.
C | Expand availability of offerings to reflect the needs of all students | 1 | Distance education FTES—increase offerings from 1,571 in 2017-2018 to 3,189 by 2023-2024 4 | Y | Provide two additional DE certification training sessions. Offer more sections of DE. Collect data on new DE courses to monitor student success. Establish Math testing center. | Dean of DE | Dean of Distance Education, Deans and Chairs of respective areas, Academic Senate President | Four sections of the DE Certification Course were completed in 2019-2020. There were 38 more DE sections offered in Spring 2020 than Fall 2020. DE course data success rates to be analyzed. The Math testing center was not established. | 100% | Continue to offer more courses in DE. Continue to offer more professional Development in DE. Create student online support center. Diversify full time and part time DE faculty [Theme 2] Provide culturally responsive tutoring and student support for DE courses [Theme 4] |  | Add online DE certicate for critical studies for FTMA. Increase to 1,000 first time freshmen into college strategies and career and life planning online courses. Increase the number of short-term sections, especially hybrids, on campus. | Instructional Technologist/Designer
|  | 2 | Friday, weekend, and evening sections—increase as total from 340 in fall 2018 to 406 by fall 2023 | Y | Add 6 Saturday hybrid sections as part of PACE | Dean of IE | Dean of PACE, Deans and Chairs of respective areas, Academic Senate President | Expanded PACE to three new degree programs | 100 | Continue adding Saturday sections for PACE if COVID allows, though prioritize online as preferred by PACE students |  | Add three disciplines as part of PACE. Consider Accounting, Graphics, Cyber Security,
|  | 3 | Short term sections—increase from 249 in fall 2018 to 304 by fall 2023 | Y | Add 44 short term sections as part of PACE | Dean of IE | Dean of PACE, Deans and Chairs of respective areas, Academic Senate President | Expanded PACE to three new degree programs | 100 | Continue growing PACE with new cohorts and continuing cohorts. Work with IE to study whether 8 week courses have higher success rates than 16 week courses. |  | Continue to add short-term sections to fall, spring and summer schedules.
|  | 4 | Offer a winter intersession by 2023 (if district switches to compressed calendar) |  | Offer 4 week winter session courses in 2020. | VPAA | Deans and Chairs of respective areas, Academic Senate President | pilot completed. Condensed calendar work ongoing | 100 | continue work on condensed calendar. continue scheduling 4 week session in January |  | Review data on four-week class success rate from Spring 2020; consider revisions, changes.
*Themes
Theme 1: Diversifying the Curriculum to Include the History and Culture of Black, Indigenous, LatinX, Asian and other People of Color
Theme 2: Hiring of Staff, Faculty, and Managers that Represent the Racial and Ethnic Diversity of our Student Population
Theme 3: Leadership on Racial Issues and Civic Engagement
Theme 4: Providing Culturally Responsive Student Services such as Counseling, Tutoring, Mental Health, etc

## SD3 STUDENT SUCCESS
STRATEGIC DIRECTION #3
STUDENT SUCCESS
Moorpark College will provide the resources and opportunities needed to support the academic and career success of all students
| GOAL | METRIC |  | PRIORITY FOR 2019-2020 | ACTIONS 2019-2020 | POINT PERSON | LEAD(S) | END OF YEAR STATUS | % COMPLETE | ACTIONS 2020-2021 | LEAD(S) | PLANNING RETREAT ACTIONS BRAINSTORM 2020-2021 | PRIORITIZED RESOURCES ALLOCATED 2020-2021 | GAP
A | Provide financial support for low-income students | 1 | Students filling out FAFSA/CADAA—increase from 11,870 in 2018-2019 to 13,330 by 2023-2024 | Y | FAFSA shift to onboarding with student support. Adopt FA application is mandatory 2. Target feeder high schools with below 53% statewide completion rate with additional application assistance and follow up 3. additional promotion of weekly Wednesday workshop hands-on assistance available on campus 4. each lead to visit assigned target feeder hs weekly for one hour window to increase apps 11% | Financial Aid Officer | Guided Pathways Dean, Faculty Lead, Financial Aid Officer & Financial Aid Specialists | President Sokenu held forum with local schools where they indicated they are very satisfied with the FAFSA /CADDAA support they receive from MC. | 10% | 1. Developed new data reports in Argos to identify and pursue HS students with incomplete FAFSA files. 2. Developed new data reports in Argos to identify and pursue students with current aidyear FAFSA but no upcoming aidyear FAFSA and reached out to advise and assist students to encourage completion. 3. Increased outreach events at local feeder schools to increase FAFSA and CADAA. 4. Explore if there are ways to compel students to complete FAFSA in enrollment process or in HS. Provide culturally responsive students services in financial aid [Theme 4]
|  | 2 | Sections with zero and low textbook costs—increase zero textbook cost sections from 328 in 2018-2019 (including summer 2019) to 769 by 2023-2024, which will represent about 20% of all sections; increase low textbook cost sections to 1,192 by 2023-2024, which will represent about 31% of all sections | Y | Hire ZTC Coordinator, complete ZTC/OER grant . enhance current textbook lending libraries in the VRC and the college library | Dean of DE | Success and Equity committee Co-Chars, Dean of DE, DE Coordinator, Library | The ZTC Coordinator was hired for the academic year. The IOCP grant was extended to December 2020. The grant is on track for completion. The textbook lending library was expanded in 2019-2020. | 75% | (1) Complete the IOCP Grant by December 2020., (2) Hire a ZTC Coordinator for the 2020-2021, (3) Expand the coordination with OER Materials with Library Services, (4) Assess textbook lending program infrastructure |  | ZTC - The Coordinator should continue to seek funding from campus and state sources such as Perkins and Strong Work Force to meet its current goal of 30 faculty participants. To seek to increase the goal by 30 or more additional faculty. Identify free to low-cost supplemental resources (question banks, assignments, instructor manuals, powerpoint slides, etc.) that align with adopted OERs/ZTCs that faculty can easily integrate into their OER/ZTC friendly courses. Alternatively, leverage MC Instructional Technologist/Designers to create OER/ZTC aligned materials within Canvas LMS.
|  | 3 | Emergency micro grants disbursed—increase annually to $10,000 by 2023-2024 |  | 1. implement form for students to apply fall 2019 2. outreach to campus community to explain form & process 3. fa staff to process daily as received 4. promote & ensure ongoing funding. 5. begin a low-key donor campaign from faculty/classified direct from paycheck. Also moving other donors to online process. 6 Evaluate the goal to go in perpetuity. | Financial Aid Officer | Financial Aid Specialists, EFG workgroup | established 3 emergency funds and distributed >$215,000 to students in direct emergency aid. | 95% | 1. established EFG grant with donations from ASG and financial aid and promoted to students and faculty largely by WOM. 2. Applied for and received >2.5 million in CARES funding and distributed to students per executive team model continuing into 2021. 3. Received $100,000 in funding from AB19 to distribute to DI students in the form of emergency aid and >$200,000 distributed to AB540 students. |  | Finding and distributing additional emergency funds for AB-540 students. For example, the Federal CARES Act doesn't provide assistance for AB-540 students. Perhaps, an additional emergency micro grant can be established for AB-540 students.
|  | 4 | Scholarships—increase dollar amount of scholarships awarded from $174,000 in 2017-2018 to $200,000 by 2023-2024 |  | Establish donor database and populate donor prospect lists | Director of Advancement and Marketing | Director of Advancement and Marketing, Foundation Board | Total scholarships awarded in 2019-20: $173,592.. Purcahsed Boomering software. | 20 | Populate donor list in Boomering and establish foundation campaign to increase money for scholarships. Establish baseline for $ amount of unclaimed scholarships. Work with IE to dissagregate scholarship recipients by ethnicity to see if it matches college demographics. |  | To strengthen the campus foundation so that it establishes activities and sources to increase scholarship funding. | ?Marketing Specialist?
B | Improve and expand educational support programs for all students | 1 | Teaching and Learning Center—increase visits from 10,800 in 2017-2018 to 11,880 by 2023-2024, with a focus on increasing visits from disproportionally impacted students | Y | Increase tracking of students ID with database. Increase use of drop-in tutoring by equity-related programs (VRC, Athletics, Foster Youth, ACCESS and EOPS); TLC provide academic support workshops] [Equity Plan] | Dean of TLC | Dean of IE, TLC | 12,828 visits occured in the 2019-2020 academic year. Data shows that a greater number of DI students attending the TLC. | 100% | (1) Work with architect to expand Math and Science Center, (2) Ensure students are aware of online tutoring efforts through increased communication and marketing efforts, (3) Integrate tutoring in the Student Support Hub in Canvas Provide culturally responsive tutoring [THEME 4] Work with IE to see if TLC visits ethnicity match ethnicity of college. |  | Establish a central Student Support Hub within Canvas to connect students to the Teaching and Learning Center. Embed access to drop-in remote tutoring services within the Support Hub as well as appointment options for alternate hours to accommodate students with different schedules. Continue on the improvement of wayfinding/signage around campus.
|  | 2 | Course embedded tutors—increase from 25 in 2018-2019 to 50 by 2023-2024 | Y | Increase placement of CET. Faculty PD. TLC provide tutorial workshops | Dean of TLC | TLC, faculty | There were 35 CETs in Fall 2019 and Spring 2020. Faculty received an orientation training on how to work with a CET. Workshops were provided to support CET work. | 100% | (1) Continue to thoughtfully expand CETs based on student success data, (2) Expand the role of CETs to occur in DE formats in respones to COVID-19 and assess effectiveness on student success [THEME 4] |  | Seek College Reading and Learning Association (CRLA) certification (if it is not already adopted) for Moorpark College tutor program/training. Resource: https://www.crla.net/index.php/certifications/about-crla-certifications Continue on the improvement of wayfinding/signage around campus.
|  | 3 | Guided Path to Success (GPS) students—increase from 120 in fall 2017 to 550 by fall 2023 |  | Connect and align with Guided Pathways Student Support Design team; expand GPS to be for all (100%) incoming freshmen. Have Spanish speakers at orientations. | Dean of GPS | Guided Pathways Student Support Design Team , Outreach | Program has undergone name change from GPS to FYE - First-Year Experience. We are at 75% completion for aligning with Gudied Pathways and are part of the Student Support Design Team and working collaboratively with the GP lead to create support circles. | 75 | We will continue to provide coaching services to all students at the college. Counseling services will remain specifc to FYE students based on hours available for our counselors. We will expand our services beyond the first-year into the Second-Year Experience so the students at MC can be supported throughout their time with us. Our goal is to provide FYE services to all first-time freshman entering the college which will require full-time staff. Our goal is to maintain a cohort of 400 sutdents for this academic year [THEME 4] |  | Establish a central Student Support Hub within Canvas to connect students to FYE (previously GPS). Explore the possibility to include part-time students and not only full-time (to include students who start half-way throught the semester with accelarated courses or drop some courses when they start the program) Consider extending services to students who did not participate in the program previously Continue on the improvement of wayfinding/signage around campus.
|  | 4 | Peer mentoring—increase to 2,000 students receiving mentoring by fall 2023 |  | Connect with Guided Pathways Student Support Design team. Explore funding feasibility. Set up as course for credit | GP Coordinator | Guided Pathways Student Support Design Team | designed care circle | 20 | Implement care circles in Fall for Spring [THEME 4] |  | Establish a central Student Support Hub within Canvas to connect students to Peer Mentors. Explore the possibility to include part-time students and not only full-time
C | Improve and expand academic counseling services for all students | 1 | Customized education plans—80% of first-time students will complete a customized education plan by 2023-2024, with a focus on disproportionally impacted students | Y | Complete Guided Pathway Mapping. Input into Degreeworks. Look at Scheduling software. .a coordinated effort. | Dean of Counseling, GP Coordinator | GP Design Teams | Mapping completed, degree works to be done over summer. | 70% | Complete mapping in degree works. Work with counseling to utilize maps to support ed plans. Increase diversity hiring of full-time and part-time counseling faculty [THEME 2] Provide culturelly responsive training to student services staff [THEME 4] |  | Implement Guided pathways maps and make them available to students. Input 20% of the maps into degree works. Establish online drop-in services through Cranium Cafe. Increase accessiblilty for students through virtual appointments, workshops, and forms. Increase the personal/social support along with giving them appropriate college strategies so students can successfull transition to online learning. To create a process for students to obtain wifi and laptop access funded College especially to students that don't have this already. Creating a canvas shell for all incoming student to deliver important information for new students. Develop a non-credit (free) college successs that first time students are directly enrolled in. Test out special program such as GPS by auto-enrolling these students in appropriate courses for first term. | Full-time Counselor
|  | 2 | Completion of 15+ units per semester—decrease equity gaps for disproportionately impacted groups by 40% by fall 2023, and fully close achievement gaps by fall 2026 |  | Continue activities for the 15 to finish campaign including contacting students who enrolled in 12 or more units. Measure effectiveness of campaign. Explore whether a campaign for 30 to finish may be more effective adding in summer. | Dean of Counseling, Marketing | Financial Aid Officer, Dean of Counseling, Director of Marketing | Students were contacted but measurement was not taken yet to gauge effectiveness. | 80 | Continue contacting students for 15 to finish campaign, and measure effectiveness. Work with IE to measure whether phone calls increased students who enrolled in 15 compared to a control group. [THEME 2] [THEME 4] |  | Broaden and expand marketing for this campaign...put it canvas shell and survery students. | Marketing Specialist?
D | Promote civic engagement, advocacy, and a global perspective | 1 | Sections with content connected to civic engagement—increase to 150 by fall 2023 |  |  | Julius |  | n/a--no action completed in 2019-2020 | n/a | Groups working on Social Justice themes to brainstorm ideas for how to increase civic engagement in curriculumn and provide more leadership opportunities for students on social justice issues. Also, fully implement ADT in Social Justice [THEME 1] [THEME 3] |  | Bring this request to academic senate. Propose as a question for the Curriculum Work group.
|  | 2 | Students engaged in advocacy through co-curricular activities—increase to 80 by 2023-2024 |  | 1) Promote voter registration via MC-branded TurboVote page during campus-wide civic engagement events like Constitution Day; 2) Host at least one 2020 Census information booth on campus to educate students on importance of participating in census; 3) Increase voter turnout in ASMC elections by enhanced marketing and promotional efforts. | Dean over Student Activities + Associated Students (ASMC) | Student Activities Specialist; Associated Students of Moorpark College (ASMC) | (1) Campus hosted Constitution Day on 9/17/19, and collaborated with the Make Moorpark Count Committee on Animal Census Days at the America's Teaching Zoo on 2/8/20 and 2/9/20. (2) Invited Justine Fischer, Partnership Specialist -Ventura County US Department of Commerce, 2020 U.S. Census to present at the Inter-Club Council on 11/6/19, and to table to outreach to MC students on 2/10/20 and at the Spring Festival event (which was canceled) on 3/14/20. (3) ASMC conducted 30+ in-person and virtual classroom presentations to promote Associated Student government elections. | 100% | (1) Promote online voter registration and share deadlines for registering to vote in fall election; educate students about how to request absentee ballots if applicable. (2) Host online activities for Constitution Day (9/17/2020). (3) Increase number of students involved in advocacy for anit-hate and BLM initiviates including leadership and advocacy workshops and host town halls [THEME 3] |  | Clearly define goals (Who are the 80) so we can measure this outcome. Expand/continue opportunities for students to participate in civic engagement. Getting involved involved in food pantry. In light of COVID-19, how to we continue with civic engagment due to social distancing practices. Address issues of social distancing practices with students and faculty...how will we proceed upon the return.
|  | 3 | Study abroad participants —increase from 12 in 2016-17 to 87 by 2023-2024 |  | Marketing. | VP AA | International Studies Committee, Dean | established several study abroad options | 90 | Re-evaluate after COVID-19 |  | COVID? How will this change our goals.
|  | 4 | International students—increase from 105 in fall 2017 to 315 by fall 2023 |  | Expand partnership with international recruiters. | Director of Outreach and International Students | Director of Outreach and International Relations | Events got cancelled due to COVID | 66% - attended 2/3 events scheduled. However the last event was the most imporant one - NAFSA 2020 | Participate in as many live conferences as possibles. They are not all in place yet, but are coming up. Offer and create live events on Facebook and Instagram. Already did a couple in Brazil and India. Participate in at least 5 online recruitmet fairs. Attend NAFSA 2021 and ICEF. Complete traveling abroad plan as soon as travell is possible. Work on possibly creating MC's own ESL program as many languages schools have now closed and won't reopen. |  | COVID? Support new international students that are coming from universities, ESL programs that are closing. We can look at marketing to these students looking for a college program.
E | Provide opportunities for students to link their academic programs to their career interests | 1 | Counselors trained and involved in career counseling—90% of counselors by 2023-2024 |  | Establish GP Design Team, CareerCounselor training | Dean of Counseling. GP Coordinator | GP Design Teams, Counselors | Design team established, but training not done | 50 | Conduct Career Counselor training |  | Counselors to develop relationships with industries to develop shadowing or touring opportunities. | Full-time Counselor
|  | 2 | Career assessment taken by students—increase from 821 in 2017-2018 to 2,463 by 2023-2024 |  | Connect with Guided Pathways Student Support Design team to add this into the 1st year experience they are designing. Prioritize career assesment tools. Map out how this work flows "carreer buckets" | GP Coordinator, Dean of CTC | Career Transfer Center, GP Design Team | establish Guided Pathways Career Pathway Coordinator | 80 | hire Coordinator, work with CTC to increase survey use and career options counseling |  | Expand career buckets to expand opportunities that students may not know exist.
|  | 3 | Career center workshop attendees—increase from 761 in fall 2018 to 2,283 by fall 2023 |  | Increase resume, interview workshops, Increase job placemetn | Dean of CTC | Career Transfer Center | strong work on soft skills, resume workshop, good job placment | 90 | Increase resume, interview workshops, Increase job placemetn |  | Have counselors and career center personnel come to classes and speak to students. Have campaign to increase awareness and exposure of these workshops. Have instructors share the information directly with students. Use flex activities to train instructors on sharing career information
|  | 4 | Internships—increase from 148 in fall 2018 to 444 by fall 2023 |  | Continue efforts to reach out to industry to identify sites for additional M80 internships. For new curriculum, explore making M80 a required course similar to CNSE or Game Design. | Dean of CTE | Dean of CTE and Career Transfer Center | very successful | 100 | Continue efforts to reach out to industry to identify sites for additional M80 internships. For new curriculum, explore making M80 a required course similar to CNSE or Game Design. |  | Have industry professionals come out to speak with students about career options. Career specific requirements including physical and mental requirements for career path
|  | 5 | Research opportunities—increase the number of students that enroll in courses that offer research opportunities with universities from 10 in 2018-2019 to 50 by 2023-2024 |  | Increase undergrad research opportunities | VP AA | STEM faculty | increase opportunites with 2 new grants with CSUN | 70 | continue to promote research opportunities, possibly with HSI grants if they are awarded |  | Utilize the honors program to generate additional research opportunities. Market directly to companies and seek additional research opportunities for our students. Have a speaker come in to classes or tour various industry facilities.
F | Provide opportunities for student connection | 1 | Student clubs - increase student membership from 567 in fall 2018 to 652 by fall 2023. |  | 1) Host at least one Club Rush event per semester; 2) Collaborate with Outreach and GPS offices to speak about clubs at orientation programs during Summer and/or Fall 2019; 3) Train club leaders to outreach to faculty and deliver presentations about their organizations to appropriate classes during the fall semester; 4) Train ASMC leaders to outreach to faculty and deliver presentations about getting involved on campus to appropriate classes during the year. | Dean over Student Activities + Associated Students (ASMC) | Student Activities Specialist; Associated Students of Moorpark College (ASMC) | (1) Hosted two 2-day Club Rush events, first in the fall on Sept 10/11, 2019 and second in the spring on Jan 28/29, 2020. (2) Presented about student life during fall 2020 New Student Welcome and in Professor E.Beltran's College Strategies courses Oct 16/17, 2019. (3) This training for club leaders did not occur. (4) ASMC delivered presentations, especially during spring 2020, to promote ASMC and clubs. | 75% | 1) Work with ASMC to innovate ways to host virtual club rush for Fall 2020. 2) Identify at least one student to serve on each campus shared governance committee for the entire year. 3) Help the ASMC Programming Committee financially support club activities (e.g., field trips, conference attendance, on-campus events, and others) so clubs are more enticing and enriching for students. 4) Help club leaders identify effective ways to outreach to students while working remotely. 5) Support student clubs involved in anti racism and social justice [THEME 3] |  | Reach out to students to be active participants to be active in environmental committee and sustainability programs. Interactive involvement with students like wayfinding project. Have campuswide project to have hands on activities to serve others in the community.
G | Maintain standards of intellectual rigor and creativity | 1 | SLO discussions— increase the number of programs that hold discussions for SLO relation to academic rigor in juxtaposition to: assignments, norming, rubrics, grading, and/or assessment of the outcomes to 47 in 2023-24 |  | Work with SLO Committee to figure out specific examples of what these discussion could look like and process to capture those discussions. | Dean of IE | SLO Committee, SLO Coordinator | Pivoted focus to migrating to eLumen, which will help to better track these conversations. | 50 | Work with SLO Committee to figure out specific examples of what these discussion could look like and process to capture those discussions. Explore adding social justice learning outcomes in all courses. [Theme 1] |  | Elumen will help facilitate data tracking and hopefully spark discussions: Curriculum updates encourage disciplines to revisit the CLOs, SLOs, etc.--updates will be a record
|  | 2 | Distance education success rates—reduce gap between on-ground, hybrid, and online classes to 2.0 percentage points by 2023-2024 |  | Continued professional development for faculty in DE. Continue CVC-OEI work to align more courses with their rubrics. | Dean of DE | DE Coordinator, DE Dean, Instructional Tech/Designer | To date, we have three CVC-OEI aligned courses. We have an additional 12 courses that went through the review process through the IOCP grant. Moorpark College has applied to be a Local POCR (Peer Online Course Review) campus. Aligned courses reduce the gap between on-ground and online. | 75% | (1) Obtain Local POCR certification, (2) Establish a POCR process with DE Subcommittee to approve new courses, (3) Obtain funding to support POCR reviews, (4) Assess aligned courses versus non-aligned courses (5) work with IE to study success in sequential coursesc comparing online vs face to face (6) study synchronous vs asynchronous courses (7) Continue laptop lending program for students and employees and explore how to expand internet access to more students. (8) Reduce DE caps to 40 and increase sections to offset. |  | Analyze data from this semester? lots of data but not a "normal" environment. Impact of CVC-OEI grant on development of online courses to be campatible the CVC-OEI rubric--look at success rates for those that meet the rubric versus those that do not (ideally within same discipline so have a control group). Explore OER/ZTC success rates versus traditional texts. Comparison of delivery method in terms of email vs Zoom vs Canvas (teaching online vs teaching an online class). Continue DE training. | Instructional Technologist/Designer
|  | 3 | Honors students—increase from 210 in fall 2017 to 360 by fall 2023, with a focus on increasing participation by disproportionally impacted students |  | Direct mail postcards to potential Honors students. GPS orientation to include Honors. Complete curriculum on additional Honors courses. | Dean of Honors | Dean of Honors, Faculty Coordinator of Honors, Curriculum Chair | Postcards sent and other outreach. | 100% | Continue to promote Honors with outreach activities |  | Adding honors link to all the GP program maps--more accessiblity. More advertising to students: promote during campus event such as club rush, etc. Encourage faculty to discuss honors in class and providing links in syllabus, etc. Add search for honors in schedule of classes. Include honors info in packet for high school students for career day.
|  | 4 | Academic integrity—increase to 150 by 2023-2024 the number of faculty that utilize technology such as Turnitin.com and Proctorio to minimize cheating |  | Proctoria professional development. Testing Center | Dean of DE and Conduct | Professional Development Committee | Proctorio is funded through the CVC-OEI through December 2020. Due to COVID-19, more faculty have utilized Proctorio with mixed reviews. Proctorio training was provided to faculty by ITDs. | 50% | (1) Determine academic integrity software and ongoing funding source (2) Provide training for faculty, staff, and students on the use of software |  | Keep professional development of such programs such as Proctorio and Turnitin.com. Inform students of requirements for classes that use Proctorio; one solution is syllabi posted on schedule of classes. Schedule of classes class notes could include this information. Explore a campus-wide testing center. | Instructional Technologist/Designer
|  | 5 | Faculty trained in cultivating exploration and expression within a creative praxis—increase to 50 by 2023-2024 |  | Support conferences . Prof development | Dean of AMC | Prof Deve Committee, Faculty | Limited conferences due to COVID | 20% | Explore how to increase expression and creativity within the online environment Explore how to train faculty to help students express social justice in a creative praxis [Theme 1] |  | Plan PD at MC. Educate faculty on definition, goals, and benefits..eg. how to add an assignment in class to cultivate exploration and expression within a creative praxis. Create guidelines for creating such assignments and rubrics for grading. Ex: making videos instead of essays?
*Themes
Theme 1: Diversifying the Curriculum to Include the History and Culture of Black, Indigenous, LatinX, Asian and other People of Color
Theme 2: Hiring of Staff, Faculty, and Managers that Represent the Racial and Ethnic Diversity of our Student Population
Theme 3: Leadership on Racial Issues and Civic Engagement
Theme 4: Providing Culturally Responsive Student Services such as Counseling, Tutoring, Mental Health, etc

## SD4 CAMPUS SAFETY AND WELLNESS
STRATEGIC DIRECTION #4
CAMPUS SAFETY AND WELLNESS
Moorpark College will provide an environment that promotes both safety and the wellness of all its employees and students
| GOAL | METRIC |  | PRIORITY FOR 2019-2020 | ACTIONS 2019-2020 | POINT PERSON | LEAD(S) | END OF YEAR STATUS | % COMPLETE | ACTIONS 2020-2021 | LEAD(S) | PLANNING RETREAT ACTIONS BRAINSTORM 2020-2021 | PRIORITIZED RESOURCES ALLOCATED 2020-2021 | GAP
A | Increase campus safety | 1 | Inclusive emergency notification system—implement by 2023-2024 | Y | RFP, impliment system | Dan | Dan Watkins from District, IT Director, Facilities Director | The required emergency notification system servers have been built and configured. The client software has been installed on several computers on the various campus networks. Communications testing between the servers and clients has begun. | 15% | Conduct additional testing of communicatios from the various Moorpark College campus networks to the Emergency Notification System (ENS) server. Install the ENS client software on all staff computers. Install the required infrastructure to support the displays, speakers, and strobes. Install the displays, speakers, and strobes and test. Provide training to all staff on the ENS client software and the mobile app. |  | Installation and implementation of the new campus-wide Emergency Notification System | ?Marketing Specialist?
|  | 2 | Active shooter/fire/earthquake drills—conduct one campus wide drill and three table top drills per year for each by 2023-2024 | Y | Map responsibilities. Sylvia coordinates with Chief. Earthquake-Great Shake Out Day. Active Shooter, coordinate with PD. Fire, schedule once a year. Reestablish County Services with MC and monthly meeting. Develop a plan. Create a position or add responsibilities | Silvia | VPBS, Director of Facilities, Classified Senate, Campus Police, Sam, President, Campus Commitment, County EMS | Participated in Great Shake Out Drill; Conducted monthly Emerg. Response Team mtgs; Began table-top discussion of active shooter scenario | 20% | Map responsibilities of 'Campus Emergency Manager' posn (PE) and hire; Reestab relations with VC Emergency Services - invite to mtgs; Develop a plan for fire response; schedule one (1) drill/yr as soon as it is safe to return to campus; Complete one (1) table-top emergency drill; Continue Great Shake Out participation to the best of our ability with remote employees. |  | Jennifer Clark will coordinate for Emergency Planning and Coordination
|  | 3 | Building monitors—complete building monitor plan by Fall 2019 and run one drill a year from 2019-2020 | Y | Define and train building monitors. Supply Equipment. Partner with Local Emergency Services. Night version of training. | VPBS | Sam, Sylvia, John, Dean of other duties as assigned | Building monitors identified | 10% | Communicate widely to increase awareness of identified Building Monitors and their responsibilties . Train and supply equip to BMs. Involve local emergency services orgs to build relationships |  | Recommendation--During current crisis have custodians share building monitor responsibilities with current building monitors to increase coverage. Recommendation--Increase communication/postings such that there is campus wide awareness of who the building monitors are.
|  | 4 | Work-space preparation—increase number of employees implementing training in their classrooms/workspaces at the start of each semester to 310 by 2023-2024 | Y | Training and Professional Development. Functional training on classified CERT. Partner with local emergency agencies for professional training search and rescue. Need baseline to determine if workspace. Oleg's office will collect data | VPBS | Safety Committee. EOC | Emails send to campus at beginning of semester reminding eveyone of emergency preparation activities to conduct in classroom with students & in work spaces; baseline data not collected; no search & rescue training conducted | 10% | The following action are contingent upon faculty and students returning to campus: Collect baseline data for work-space preparation; identify faculty leads to review/encourage preparation process in classrooms; identify managers/staff leads for office spaces; conduct division/department training and document for future use |  | Recommendation--Begin discussions regarding systematic division wide building/classrooms/workspace management during emergency situations (safety considerations, escape routes, communications systems) such that there is knowledge of all facilities that are utilized by the division by 2022. Schedule as a divsion wide training event, assign someone to take notes during the training so this information can be passed on to new division members.
|  | 5 | CERT training—increase total number of employees that are CERT trained to 20 by 2023-2024 | Y | Establish a CERT Chapter | VPSS | Sylvia and Sam | CERT training scheduled for spring 2020 canceled due to COVID-19 | 0% | Advertise all CERT training offerings in the area. Focus on identified Building Monitors, Emergency Response Team, and other willing participants to be trained first |  | Continue with establishment of a CERT Chapter
|  | 6 | Title IX training—implement training created by the Districtwide Title IX committee by 2023-2024 | Y | Tracking of communication and enforce. District tracks, Establish mechanisms for supervisory checking certificates. Supply certificate copies. Need assessment of who did not take course. | Title IX Coordinator | Title IX Coordinator | Training was scheduled to happen during the spring of 2020 but was not able to happen because of COVID-19 | 0% | New regulations are now in place that will go into affect by August of 2020. Coordinator will need to receive extenisive training on new federal regulations for the first part of fall 2020 and extend training for Title IX deputies in spring 2021 |  | Expand TIX training to student workers and club leader orientations
B | Provide support for students’ basic daily needs | 1 | Basic Needs Center (to provide guidance on housing, food insecurity, health programs, affordable childcare options, etc.)—conduct a feasibility study by 2020-2021 to explore the viability of creating this center | Y | Town Hall meeting topic. Examine funding and feasibility study | Dean of Counseling | Basic Needs Committee | Presented to various stakeholders, identified location, presented to foundation | 100 | Launch Basic Needs Center |  | Basic Needs Work Group members presented at Dean's Council, Academic Senate, FTCAP, Classified Senate and the SEA Committee. Proposing that the "Poly Room" become the center with a proposed name "Raiders Central." This work group has surveyed students and looked at the data out there which supports that there is a need for a central location. Funds have been identified; waiting for approval/presentation. We would work in parntership with Ruben Castro Pantry. Large upscale of supplies (cloth masks, etc.) and staff support; retrofit some of the drinking fountains to portable hand washing stations; expand food pantry hours and merchandise to include clothing and toiletries. | PAWG: "Funds to update an existing, underutilized space into a functional Basic Needs Center" - (how much?)
|  | 2 | Fitness Center—conduct a feasibility study by 2020-2021 to explore the viability of offering open labs to students without registering for a class |  | Feasibility study | Dean of Kin | Dean of IE , Dean of Kin | This feasibility study will occur in 2020-2021. | 0% | Conduct the feasibility study with the KIN faculty. |  | Expand the Free Personal Trainer Fitness Program to include currently enrolled students. Explore embedding a stretching exercise into all CANVAS, ConferZoom. It is suggested that students take a Fit Lab class to learn how to properly exercise in the fitness center (machinery, etc.) Once this class is successfully taken, students may then use the fitness center during open fitness center hours. Encourage all division and departments to input a blurb (similar to the blurbs mandatory regarding ACCESS and the No Smoking Policy) regarding mental, emotional and physical health of students and the resources available to them. Vetted through Wellness and Safety Committee. For faculty and staff to use the equipment, a one time meeting with a Student Personal Trainer would be encouraged. This "training" could be used for flex hours for faculty and release hours for classified staff. | Kin/ICA full-time Women's Basketball Head Coach
|  | 3 | Food outlets—provide access to hot and nutritious meals for students throughout the instructional day (8am to 9pm) by 2023-2024 |  | Evaluate food outlet options | VPBS |  | RFP prepared (but not yet flown) by T. Cobos for contracted food services | 5% | Evaluate additional food trucks and/or food resources with variety/healthy options when it is safe to return to campus; Develop a food voucher system for students in need |  | Develop a voucher system for food trucks/other food resources for students in need. Bring more food trucks/other food resources to campus with a variety of hot and healthy options.
C | Provide professional development for faculty and staff to be able to recognize and support students with mental and physical health challenges | 1 | Mental Health First Aid Training including suicide awareness—increase to 100% of full-time and 50% of part-time faculty trained by 2023-2024, and 100% of part-time faculty trained by 2028-2029 | Y | Mental Health training, implement training, K-12. Add classified staff. | Lisa | Health Center | Did various workshops on suicide prevention, also social media posts outreach efforts, and recieved a grant | 100 | Provide culturally responsive mental health training to faculty and staff [THEME 4] |  | Provide testing for Covid-19. Provide additional support for students effected by the pandemic including mental and emotional assistance. Establish a formal protocol for suspected cases of infected individuals and disinfection. Continue to offer faculty Mental Health First Aid Training. $29 additional charge to have the training online now per individual. Offer QPR Suicide Prevention Training online to faculty, staff and students.
|  | 2 | CPR trainings—increase number of faculty and staff trained in CPR from 13 per year in 2018-2019 to 64 per year by 2023-2024 |  | Increase training | Dean of Kin |  | CPR trainings were interupted by COVID-19 | 25% | CPR trainings will resume when it is safe to return to campus. |  | Four trainings were conducted successfully before the pandemic. The initiative to get all building monitors trained and re-trained in CPR as needed will continue. This will be open to all faculty and staff.
*Themes
Theme 1: Diversifying the Curriculum to Include the History and Culture of Black, Indigenous, LatinX, Asian and other People of Color
Theme 2: Hiring of Staff, Faculty, and Managers that Represent the Racial and Ethnic Diversity of our Student Population
Theme 3: Leadership on Racial Issues and Civic Engagement
Theme 4: Providing Culturally Responsive Student Services such as Counseling, Tutoring, Mental Health, etc

## SD5 ORGANIZATIONAL EFFECTIVENES
STRATEGIC DIRECTION #5
ORGANIZATIONAL EFFECTIVENESS
Moorpark College will ensure it has the organizational framework to fulfill the strategic directions within its Educational Master Plan
| GOAL | METRIC |  | PRIORITY FOR 2019-2020 | ACTIONS 2019-2020 | POINT PERSON | LEAD(S) | END OF YEAR STATUS | % COMPLETE | ACTIONS 2020-2021 | LEAD(S) | PLANNING RETREAT ACTIONS BRAINSTORM 2020-2021 | PRIORITIZED RESOURCES ALLOCATED 2020-2021 | GAP
A | Improve campus physical infrastructure, with a focus on sustainability | 1 | Complete facilities projects that are fully funded and aligned with the Facilities Master Plan |  | Update Facilities Master Plan to reflect current Education Master Plan. -Completed facilities and ground | Director of Facilities, Maintenance & Operations | Director of Facilities, Maintenance & Operations, VP Business Services | A matrix has been completed that that links the comments gathered at the 19-20 Planning Retreat to the Education Master Plan finalized the the same event. This matrix was recently approved at the May 29, 2020 F/TCAP meeting. | 50% | Append the approved matrix to the Facilities Master Plan. Incorporate the the facilities improvements included on the matrix into the body of the Facilities Master Plan. |  | Completion of the facilities master plan will be presented to the FTCAP committee in late April. Looking at campus infrastructure to facilitate Social Distancing. Zoom and inclass hybrids? | Facilities funded: 6 x High requests: Speakers in PAC; cinder-block dugouts; Main stage speaker cluster; ?rigging system in PAC; new speakers for Mainstage; replace exterior doors of Music Bldg. 14 x Medium requests: EATM passenger van; Wildlife Theater sound booth; boom lift for M&O; upgrades to EATM animal fences;Kin/ICI storage unit for track and field; pole vault pit cover; CDC climbing structures and cushioning; PAC CATS cables; new pianos; new Kin hammer/disc rings; kiln auto-controller; new EATM shade cloth; control consoles for FTVM to be ADA compliant; 4 studio lighting kits. 27 x Low requests . . ..
|  | 2 | Complete technology projects that are fully funded and aligned with the Technology Master Plan |  | Producing new Tech Master Plan. Light up Tech with WiFi. FTVM decent classroom. Break down priorites and funding. New signage, Dan to add topline items. Repairs and modifications | Dan |  | Added 33 wireless access points on campus. Created new computer lab for FTVM. Added 2 additional laptop carts on campus. Upgraded the software applications in all labs. Refreshed computers for faculty and staff. Complete grant funded audio visual upgrades in Tech building. | 75% | Complete audio visual equipment installations in FH classrooms. Complete refresh of computers in the photo lab. Complete ENS. Add video into classroom to implement hyflex. |  | This plan has been revised by Dan which was presented to the FTCAP committee in March 2020. | List some/all of TRAWG funded items here?
|  | 3 | Develop a Sustainability Plan by 2019-2020 |  | Complete the Campus Sustainability Plan | Director of Facilities, Maintenance & Operations | Director of Facilities, Maintenance & Operations, In conjunction with Associated Students and the Campus Environment Committee | Working with the Moorpark College Associated Students, a sustainability plan framework as seen from the student perspective was developed. | 75% | Finalize sustainability plan |  | John will be presenting the Sustainability Plan on April 28th to the Fiscal Planning Committee.
B | Improve campus organizational infrastructure with a focus on inclusive decision-making | 1 | Integrated planning—investigate creation of a centralized process for resource allocation, both categorical and general funds by 2021-2022 |  | 1. Re-examine 'Decision Making at MC'; study alternate models; map dovetailing committees with overlapping charges (EdCAP/Fiscal; F/TCAP and CTE Workgroup, etc); consider how to build cooperation between these committees; update 'Decision Making at MC'. | President | President, Academic Senate, Classified Senate, Associated Students | Revised 'MC Participatory Governance Handbook' approved by Associated Students, Classified and Academic Senates, and College President, May 2020. Process put in place for Fiscal and EdCAP to hold Joint Meeting in Spring semester to review results of all resource prioritization processes in alignment with Strategic Plan and make any recommendations. | 100% | Implement and evaluate Fiscal and EdCAP Joint Meeting in Spring semester to review results of all resource prioritization processes in alignment with Strategic Plan and make any recommendations.
|  | 2 | Classified representation—increase number of classified co/tri-chairs on standing committees from 2 in 2018-2019 to 5 in 2023-2024 and increase the number of seats held by classified staff from 8.5% in 2018-2019 to 20% of committee members by 2023-2024 |  | Look at Making Decision Handbook — classified | President |  | In updated 'MC Participatory Governance Handbook' number of tri-chairs remains at two; classified reps added to Standing Committees as follows: Fiscal 2 new reps for a total of 5, in EdCAP 2 new reps, in SLO 1 new rep, in SEA 2 new reps, and in Curriculum 1 new non-voting rep. | 100% | Ensure classified co-chair positions and committee slots for classified staff are filled and those staff feel they are able to successfully engage in the committee work. |  | Classified representatin is being increased.
|  | 3 | Develop a project management structure that includes a total program cost and timetable for implementation: all new projects/initiatives will document the human, fiscal and physical resources as well as the outcome(s) required for the project over a set time period by 2023-2024 |  | Create a centralized grant application and process. Share with Admin Council and Senate. | VPBS |  | Identified possible process and staffing, but we still need to formalize the grant application process with Admin Council and Senate | 60 | Create multi year budget that includes TCO
C | Increase revenue generation | 1 | Meet annual FTES targets |  | Develop a marketing campaign for Moorpark College and for specific populations like LatinX and adult learners | Director of Marketing | Director of Outreach and International Relations, Director of Marketing, Deans and Chairs of respective areas | Hired a marketing specialist | 10 | Develop a marketing campaign for Moorpark College and for specific populations like LatinX and adult learners |  | Continue search for marketing Director. DI groups to increase enrollment, comprehensive marketing plan to possible incude channels targeting certain populations such as radio ads, direct mail campaign, social media and youtube. | Marketing Specialist
[5 empty] | Develop and market ESL program | Dean of ESL | Dean of ESL | no progress | 0 | Develop and market ESL program |  | pre Pace to build skills capacity with underserved populations to matriculate into Pace program | Marketing Specialist
[5 empty] | -Optimize course scheduled timing around the needs of students to ensure students are able to complete their programs of study -Optimize which courses are offered each semester to ensure students are able to complete their programs of study -Optimize room utilization to ensure course offerings meet students needs -Create new data reports to advise department chairs on past student enrollment patterns | VPAA | Deans and Chairs of respective areas | three term enrollment report created, schedule timing and courses were evaluated, room utilization discussions started, COVID disrupted enrollment management--dramatic increase in summer enrollment and a decline in fall enrollment. | 90 | update enrollment management plan in light of COVID |  | Need an arf like assessment for students should scheduling be nights/weekends/asynchronous? Can application be included in admissions process unavailable/available/preferred – agregrated & broken down
[5 empty] | -Evaluate software programs that allow scheduling to meet student Ed Plan requirements | VPAA | Dean of Counseling | no progress | 0 | Utilizing guided pathways, encourage students to enroll in english and math in first year, and encourage students to enroll as full-time students |  | strategic about 10/4/12 wk classes, ztc components get better at how we schedule online hard with 60/40 way to plan a really creative schedule to generate revenue all the proprietary do it- ways to differentiate to attract more students | Marketing Specialist
[5 empty] | -Explore expanding waitlist from 5 to 20 so that they can be used in decision making to offer new sections | VPAA | Deans and Chairs of respective areas | discussion was had, but no consensus on moving further | 50 | Explore feasibility of expanding hyflex courses |  | expand waitlist from 20 to 50- dashboard for all to track
[5 empty] | -Utilize classroom time to advise students on enrollment selection | VPAA | Deans and Chairs of respective areas | completed in certain divisions, in collaboration with student services | 50 | Explore ways to contact students who were dropped for non-payment to get them to re-enroll and measure the impact of that outreach in collaboration with IE. In addition to outreach, explore all other options to get students who dropped for non payment to re-enroll. |  | get them to register before they leave announce reg is open now in all classes
[5 empty] | Explore having spring start later in alignment with LACCD. | VPAA | VPAA | no progress, this is related to compressed calendar discussions | 0 |  |  | continue work group hire consultant for feasability
[5 empty] | Explore the processes the college uses when a class is cancelled or delayed to encourage students to enroll in another class. Explore ideas such as there should be a similar process used across all divisions, and that students should be automatically and immediately contacted with suggestions for similar classes in the same timeslot whether by email or preferably by phone. | VPAA | VPAA | had discussion several times to improve the process | 80
[5 empty] | Explore modifying the drop policy for non-payment. Explore ideas such as extending the periods for payment; investigating the insurance policies for non-payment that other districts use; clarifying the information on non-payment sent to students; sending out warning notices to students before being dropped; utilizing the faculty to follow up with students before they are dropped | VPSS | Bursar | extensive meetings at DAC, MC, and BOT on this issue which are continuing into 2020-21 | 80 |  |  | continue work group hire consultant for feasability
|  | 2 | Contract and community education—conduct a feasibility study by 2019-2020 |  | Conduct a feasibility study of contract and community education | VPAA | VPAA | no progress | 0 | Conduct a feasibility study of contract and community education |  | To increase revenue look at our CTE programs to increase short term training and certificates- leverage to attract new students to our CTE programs
|  | 3 | Noncredit FTES—Increase to 91 by fall 2023 |  | Expand ESL offerings | Dean of ESL | Dean and Chair of ESL, Dean of CTE, Director of International Students and Outreach | completed approved for non-credit curriculum for ESL and BIW | 50 | Expand ESL and BIW offerings |  | To increase revenue look at our CTE programs to increase short term training and certificates- leverage to attract new students to our CTE programs
|  | 4 | Grant application submissions—increase to 12 per year by 2023-2024 |  | Establish process for new grants. Submit 3 grant applications, including DHSI. Establish metric vetting process for grants. | Director of Institutional Advancement | Dean of IE, Director of Institutional Advancement | Submitted 6 grant applications including DHSI and counting 3 for Aspen | 100 | Submit 3 grant applications, though may be difficult to find grants as a result of COVID.
|  | 5 | Bond—encourage the district to place on ballot by 2023-24 |  |  | President |  | n/a | n/a | no action this year
D | Reinforce culture of continuous improvement through professional development | 1 | Faculty annually participating in professional development events—increase to 150 by 2023-2024 |  | Investigate software for PD - Professional Learning network integrated into Vision Resource Center. | Dean of PD |  | Review college of canyons process | 65% | Align PD events with social justice and online pedagogy . Collaborate with Shaun Harper's group on these events. Create student services toolkit including training on bias, have student services division read a book together like white fragility [Theme 1, Theme 2, Theme 3, Theme 4] |  | Increase PD in the area of general areas, online instructional techniques and DI. Surveying needs from faculty and staff. Strategically marketing new technology available and marketing to encourage attendance and participation. PD website used to facilitate training opportunities.
|  | 2 | Classified staff professional development events—increase from 8 in 2017-2018 to 24 by 2023-2024 |  | Increase PD offereing | Dean of PD | Classified Senate | Increased offerings for classified staff including canvas, zoom, and other tools for remote work. PD also offered on stress reduction. | 100 | Align PD events with social justice and online pedagogy [Theme 1, Theme 2, Theme 3, Theme 4]. Collaborate with Shaun Harper's group on these events. |  | Canvas training offered to classified to ease use collecting data and specific to classified needs. Additional Outlook and office training offered. Continue CPR training. Training in response to COVID-19 , including communication with students, cleanliness, issues and safety information. Building monitors training and emergency preparedness training. Classsified and staff need training in Emergency Alert System.
|  | 3 | Faculty and staff knowledgeable of universal design—increase from 43 in 2017-2018 to 250 by 2023-2024 |  |  | Dean of ACCESS | faculty and staff | Sessions on closed captioning, and website Drupal accessibility training, and zoom accessibility training, and documents training PD for faculty and staff | 100% | Integrate UDL PD sessions into FLEX and other trainings. Continue to expand training on accessibility. |  | PD on what Universal Design is, how to incorporate it to assist students, and Best Practices. | Instructional Technologist/Designer
|  | 4 | Students participating in leadership development—increase from 29 in 2018-2019 to 70 by 2023-2024 |  | Finalize structure of MC LEADS (Leadership Education and Development for Students; free workshops for students) by Fall 2019. | Dean of Student actvities | Student Activities Specialist | Finalized structure of MC LEADS version 1.0 in Fall 2019. Created website (moorparkcollege.edu/mcleads) and marketing materials and promoted program in January 2020, and implemented first workshops in Spring 2020. Planning for MC LEADS 2.0 for Fall 2020 is underway. Participants completed assessments after each workshop, which is taken into consideration for future workshops. | 100% | Work with campus marketing to enhance online marketing to reach students in online environment. Utilize club contacts and partnerships with student service units to expand participation. Continue to use spring 2020 data to inform fall 2020 and spring 2021 training topics. Support students involvment in social justice work groups [Theme 1, Theme 2, Theme 3, Theme 4) |  | Continue and expand MC Leads to include Life Skills and Leadership events. Workshops, trainings, etc. opportunities. Student Leadership responsibilities in online environment. Survey and feedback from students on interests, suggetions, improvements, etc. | Marketing Specialist
*Themes
Theme 1: Diversifying the Curriculum to Include the History and Culture of Black, Indigenous, LatinX, Asian and other People of Color
Theme 2: Hiring of Staff, Faculty, and Managers that Represent the Racial and Ethnic Diversity of our Student Population
Theme 3: Leadership on Racial Issues and Civic Engagement
Theme 4: Providing Culturally Responsive Student Services such as Counseling, Tutoring, Mental Health, etc

## Other resources
Other allocated resources | Notes
FT FACULTY:
Biology
Mathematics
Comm. Studies
English
CNSE
Counselor
Kin/ICA Women's Basketball Coach
CLASSIFIED PROFESSIONALS
Inst. Technologist/Designer
Marketing Specialist
PLANNING (PAWG)
Basic Needs Center space
FACILITIES (FRAWG) | Item number | Cost category
Speakers in PAC | 267 | high; $100k+
Baseball and softball cinder block dugouts | 62 | high; $100k+
Need to replace main stage speaker cluster (PAC) | 262 | high; $100k+
Rigging system in the PAC | 266 | high; $100k+
Replace Exterior Doors | 86 | high; $100k+ | high | 5
Zoo Van replacement (15 pasenger) | 7 | medium; $15k-$99k
Replace Wildlife Theater sound booth | 218 | medium; $15k-$99k
M&O Boom Lift - JLG 1200 | 232 | medium; $15k-$99k
Galapagos tortoise yard expansion and guard rail addition; alligator, tortoise and aviary patron fencing replacement | 215 | medium; $15k-$99k
Storage unit for track and field equipment | 230 | medium; $15k-$99k
Replace pole vault pit cover/garage | 229 | medium; $15k-$99k
Replace climbing structures and rubber cushioning on CDC playgrouns | 224 | medium; $15k-$99k
CATS cable run throughout the PAC | 90 | medium; $15k-$99k
Replacement pianos in practice rooms, classrooms, and some offices; Music | 238 | medium; $15k-$99k
New Hammer/Disc Rings for Kinesiology | 64 | medium; $15k-$99k
Kiln auto controller replacement on older kiln | 219 | medium; $15k-$99k
Replace shade cloth at Wildlife Theather | 217 | medium; $15k-$99k
Control Consoles (6) for ADA compliance for entire FTMA Program | 226 | medium; $15k-$99k
4 Profoto Studio lighting kits for photography | 244 | medium; $15k-$99k | medium | 14
Wherehouse dock leveler for M&O | 184 | low; <$15k
New 35 mm analog film cameras (10); vivitar V3800N SLR kit with 28-70mm lens (Photography) | 206 | low; <$15k
Classroom recalbing and network redesign for CNSE (LMC-139) | 152 | low; <$15k
Seat training station (4) for gym (taping area) | 176 | low; <$15k
Storage unit for track and field equipment | 177 | low; <$15k
Clorox Total 360 System electrostatic sprayer disinfectans and sanitizers (Custodial) | 155 | low; <$15k
Industrial rolling chairs (36) for make-up and costume labs (Theatre Arts) | 212 | low; <$15k
New large format view cameras (10) for photography | 207 | low; <$15k
Medium format film cameras (3) for photography | 208 | low; <$15k
Lab refrigerator for Biology | 142 | low; <$15k
Update Black Box lighting equipment (Dance) | 157 | low; <$15k
Tiple beam balances for Biology labs | 135 | low; <$15k
Privacy screening along CDC playground fence | 148 | low; <$15k
Improved housing and pool for snapping turtle (Zoo) | 115 | low; <$15k
Additional Music stands for students | 194 | low; <$15k
Projectors for T-212 and LMC-139 (CNSE) | 153 | low; <$15k
Three locking rolling cabinats to store game consoles and games (Game Design) | 172 | low; <$15k
Hoofstock barn (1) for Zoo | 114 | low; <$15k
FORUM lights repair/update (FTMA) | 49 | low; <$15k
-20 C freezer for Biology | 134 | low; <$15k
Rolling adjustable height drafting chairs (25) for Art | 129 | low; <$15k
Wookworking bench with vice for Art | 128 | low; <$15k
Adjustable rolling stools with backs for Sculpture Studio (Art) | 126 | low; <$15k
Sturdy wooden podiums (10) in all English classrooms | 158 | low; <$15k
Book return at remove outdoor location (Library) | 178 | low; <$15k
Install dimmed lighting in CDC-114 and CDC-132 | 27 | low; <$15k
Upgrade portable toilet near observatory for students during lab (Astro/Physics) | 19 | low; <$15k | low | 27
|  |  | total | 46
TECHNOLOGY (TRAWG) | Item number
Data collector for our Transit (Anthro) | 17
Capstone College/University License | 28
Access points and power over ethernet switches (IT) | 142
Apple device management (IT) | 143
Install Wi-Fi in Music Building (Music) | 167
Managed workgroup switches (14) (IT) | 141
Simple K Professional Edition Locksmith Software (M&O) | 162
Smart classroom updates for AA-136 for Art (large screen and move projector, etc.) | 23
ELMO Document Camera (2) for Astro/Physics | 32
Computers (7) for classrooms on 2nd floor of PS building (astro/physics) | 36
Laptop computer replacments (4) for CDC | 54
Smart classroom for PS-135 (Geography/GIS) | 129
Make PS-124 a smart classroom (Geology) | 130
Department computer workstation for Astro/Physics | 30
Replace old smart classroom equipment (IT) | 146
Refresh of computers (IT) | 145
Repair existing audio system in M-114 & M-109 (Music) | 169
Photocopier for VITA and other Accounting needs | 4
Large screen monitors (2) for Accounting | 6
New scantron machine (Accounting) | 7
Two large wall-mounted monitors (Accounting) | 8
Desktop computers (2) and phones (2) for Zoo | 10
Acid-free plastic bags (Anthro) | 16
Marshalltown trowels (5) for Anthro | 18
Eastwing Pick hammers (3) for Anthro | 21
Higher quality projector for T-108 (Art) | 22
Replace LCD projector and sound in AA-115 (Art) | 24
4k LED desktop monitor (Art) | 26
Desktop computer (astro/physics) | 31
Laptop for observatory (astro/physics) | 33
Pasco 550 Universal Interface (2) (astro/physics) | 35
Scantron scanning machine (Biology) | 38
Microsoft surface pro tablet for T-114 (Chem) | 49
Color printer (CDC) | 51
Computer classrom including Office 2016 and Visual Studio (CIS) | 56
300 GB Solid State drives (20) in T-212 (CNSE) | 59
Classroom recabling and network redesign (CNSE) | 61
Subscription to Safari O'Reilly Technical library (CNSE) | 63
Constanct Contact Texting Service (Counseling) | 71
Expanded Starfish capabilities (Counseling) | 74
Green Screen (Distance Ed & Instr Tech) | 83
Licenses (10) of Kahoot Pro 1 (DE/Instr Tech) | 85
Socrative licenses (10) (DE/Instr Tech) | 86
Webcams (100) (DE/Instr Tech) | 87
Headphones (100) (DE/Instr Tech) | 88
Camtasia+ Site License (DE/Instr Tech) | 89
Refine Self-placement instrument (English) | 92
Online database of film resources (Film Studies) | 93
Swipe ID device (Financial aid) | 122
Texting provider/contract (Financial Aid) | 123
Wacom (25) tablets (Graphics/Multimedia) | 133
Cimema 4D Prime R20 licenses (30) for Graphics/Multimedia | 133
Parallels Desktop 14 for Mac licenses (35) for Graphics/Multimedia | 135
3D Protyping lab (Graphics/Multimedia) | 136
Networked monochrome multiformat printers (3) for Graphics/Multimedia | 139
Network tester (IT) | 144
Uninterruptible power supplies (IT) | 148
Cabling, speakers, button panel, etc. to FH classrooms (IT) | 149
iPad (2) for International Students | 151
External music program website to complement MC Music Page (Music) | 166
Printer for Music Building | 170
Computers (3) (Operations) | 176
All in one color printer (Outreach) | 177
Epson Perfection V850 scanner (Photography) | 188
2 Braun FS120 Medium format film scanners (Photography) | 189
Refresh 3 flatbed scanners (Photography) | 195
Neurophysiology active learning demo (Psychology) | 199
Grades First (Scholarships) | 201
Software to streamline scholarship process (Scholarships) | 202
Student engagement platform (Student Activities) | 203
Temporary bleacher rental and set-up for 2 days, JumoTron rental (Student Activities) | 204
IT support from District and Starfish training and customoizaiton (TLC) | 207
CI Track (Veterans Center) | 213
Desktop computer, iPad, or Tablet (Veterans Center) | 214 |  | total | 74