ACCJC ISER Report Timeline and Leads (as of 04/27/2021)

| Month | Moorpark College | District Office |
| --- | --- | --- |
| March/April 2021 | ISER training EdCAP (Apr 27): - Review draft timeline ALO and others: - Tentative list of leads and memberships for Standard Groups for August membership meeting |  |
| Fall semester, 2021 | EdCAP: Aug 24: - Set up Standard Groups and leads - Training of interpretation of Standards - Introduction of leads to use of ACCJC documents: template for notes, sample text examples, style, etc. September/October: Groups meetings - Set up of shared Standard folders for information/ evidence/group work - Identification of possible evidence sources w/in Groups - Analysis of Moorpark’s gaps and strengths from evidence w/in Groups Sept 28: - Divide into Groups Oct 26: - Share/swop gaps and strengths from evidence between groups Nov 23: - Review combined gap and strengths analysis in EdCAP - Brainstorm QFE ideas November/December: - Group leads produce draft text for Standards from groups’ ACCJC template notes ALO and others: - Complete action items to address gap analysis recommendations from Midterm Report - Work on gaps identified from Gap analysis - Appointment of compiler/editor of ISER to produce first draft - Proto-draft of QFE produced based on strengths and gap analysis | DAC: - Review any remaining DAC gaps from Midterm reports - DAC gaps and strengths analysis - Complete action items to address DAC gaps and strengths analysis District (DCAP): - Submission and review of all gap and strengths analyses |
| Spring semester, 2022 | EdCAP: January 25 mtg: - Review draft of QFE February 22 mtg: - Identification of evidence sources w/in Groups - Review proto-draft of ISER Other committees review proto-draft of ISER: - Academic Senate - Classified Senate - ASMC ALO and others: - Dean of IE identify evidence sources from draft | DAC: - First draft of district components of ISER produced District: |
| Summer 2022 | ALO, Dean IE, and writer: - Collection of evidence within final draft (eg program plans) - ISER first draft completed - ISER first draft edited | DAC: - Final draft of district components of ISER completed Board of Trustees: - June: BoT Strategic Planning Meeting agenda item? - Aug mtg: Discussion of draft college ISERs |
| Fall semester, 2022 | ISER complete college-level approval - Communication of ISER progress to college community (FLEX Week, Convocation, etc.) - Aug/Sept - EdCAP final review - ALO with others: continue revision of final draft incorporating feedback - Sept/Oct - Academic Senate/Classified Senate/ASMC - Executive Council and Consultation Council final review Office of President: - Share draft report with college community for feedback | ISER complete district-level approval - Oct/Nov DCAS meetings - Final approval at Chancellor’s Cabinet Board of Trustees: - November Board mtg - December Board mtg |
| Spring semester, 2023 | ISER forwarded to ACCJC team (Deadline: January 15) ACCJC ISER Team training (February) One-day review by ACCJC ISER Team (early/mid March) Given our Core Inquiries President’s Office: - Preparation for Focused Site Visit |  |
| Fall semester, 2023 | ACCJC Focused Site Visit |  |
| Spring semester, 2024 | ACCJC decision (January?) |  |

From Guidelines for Preparing Institutional Reports to the Commission (for reports due fall 2020 and beyond)

https://accjc.org/wp-content/uploads/Guidelines-for-Preparing-Institutional-Reports_Fall-2020-and-beyond.pdf